## Process Outline
This is an outline of the tasks involved in taking and tracking payment for UMRA forums. Priorities are for the user to have a smooth experience, and for all money to be accounted for and annoted as such in the db, either paid to the venue, or refunded to the user, or accepted as a donation, per UMRA policies. To aid in tracking, the person doing the task is listed as Owner. Cathy or VIrgil can act as backup if requested. This outline is for regular Forums; however, any event should follow a similar outline, with these same roles assigned.
Owner | Task | Comments | backup
Host/Diane | Coordinator | Each event should have a coordinator; the Host committee serves this role for Forums. For other events someone should be assigned. | TBD for each event
Cathy (also puts them on website) | Enter & open registration | Manage Programs: At the beginning of each fiscal year, or as they become available, new programs are added to the list of programs so people can sign up for them. There are those who click on the registration links 1st thing, and we will want it to be working, so it doesn't frustrate people. | Diane, Virgil
Diane (or other) | Listed on event as contact; help with reservations; provide address for manual reservations; receive cancellations | This person 1) answers questions, and 2) helps people to register. Also 3) instructs those who do not want to use the online form, or are inviting a guest, to send a check to the proper person (Kristy). The person receiving checks should ALWAYS be the same person, for consistent handling, and so everyone knows who it is. This same person will 3) receive requests to cancel, and inform them of the cancel due date, policy on refunds. | TBD for each event
Diane | Monitor registrations | Manage Programs: View listing on website; close registration if numbers get too high; report to [board?] if registrations are unusually low. | Cathy, Virgil
Diane | Remove abandoned xactions | Manage Programs: When a transaction is Credit Card, but Processing (not Processed -- not paid), contact the member to determine if they know that they abandoned the transaction, or if they mistakenly thought they paid. This is the main reason they need to be contacted -- in case they thought they completed the trabsaction. Remove the transaction. If they wanted to pay, instruct them to try again as it did not go through. | Cathy, Virgil
Diane | Add a registration by check | Manage Programs: Add a person's name to the program Roster. Include notes on meal restrictions, whose guest if a guest, who is to receive the check and check amount. Must be marked AWAITING PROCESS until it is paid. | Cathy, Virgil
Diane | Cancel a registration and wait for replacement to refund | Add note to say they want to cancel with reservation | Cathy, Virgil
Diane | Cancel a registration and someone from waitlist replaces them to refund | Delete original transaction; create a new one with the new person's name. Comments indicate whose reservation was taken, and check to be sent to Kristi | Cathy, Virgil
Diane | Cancel a registration and refund | If someone says they cannot come, delete the transaction in the roster. Kristy may need to refund the money as well if they have paid and cancelled before cancellation due date. | Cathy, Virgil
Diane & Kristy | Track completion of records (Diane does this during reservations cycle, Kristy does this after reservations close, & as a final check at the end) | Manage Program: Make sure all registrations have been paid. Make sure all timely cancellations have been refunded. Make sure all abandoned transactions have been deleted (and member contacted - see above). This is the tieing the bow step, completing the circle, etc. ;-) This may involve using the Manage Transactions screen, as it is more flexible and you can see more. [The email confirmation that goes out depends on the ROSTER being correct as of Fri or Sat before the Forum.] | Cathy, Virgil
Kristy | Recording payment received by check | Manage Transactions: All checks should be sent to the same person (Kristy). Search for Program Fee transactions. Find the one you want. Edit, and mark Processed, Note date check received in Notes. | Cathy, Virgil
Diane | Download CSV of registrants | Manage Programs: Download for creating of nametags. If you want this CSV changed, just let me know. | Cathy, Virgil
Diane | create and print nametags | Mail merge, create PDF, send to printer, pick up from printer. | Cathy, Virgil
Cathy | send email confirmation | The Sunday or Monday before each Forum, Cathy will send a confirmation to all those are noted as paid. This depends on the ROSTER being correct as of Fri or Sat. | TBD for each event
Diane/Virgil | give extraneous checks to Kristy | If checks are received at the luncheon or at UMRA office, date received should recorded on the check (before or after due date) and given to Kristy. | TBD for each event
| To play and see what you can do | TESTING SITE: https://umra-staging.maxfierke.xyz/login
https://retirees.umn.edu/login

## Registration Tasks
This information is meant as an index to the tasks in subsequent sheets, each sheet is numbered to match a task listed here. Task sheets describe the step-by-step instructions for handling each task.
| Task | Comments
1 | Enter & open registrstion | Manage Programs: Just BEFORE the newsletter comes out. Kris may be able to give you a heads up, or tips on when to expect it. There are those who click on the registrtion links 1st thing, and we will want it to be working, so it doesn't frustrate people.
2 | Monitor registrations | Manage Programs: View listing on website
3 | Add a registration by check | Manage Transactions: date, Program Fee, $ amount, AWAITING PROCESS, member Name, (spouse?) (note about payment not yet received, or received date)
4 | Always check you work | Manage Program to be sure they showed up as expected -- even Virgil does this. If anything gets entered mistakenly it's best to catch it right away, and fix it or it will cause you confusion later.
5 | Recording payment received by check | Manage Transactions: Search for Program Fee transactions. Find the one you want. Edit, and mark Processed, Note date check received in Notes.
6 | Download CSV of registrants | Manage Programs: if you want this CSV changed, just let me know.
7 | Cancel one's registration | If someone says they cannot come. You may need to refund the money as well if they have paid.
TESTING SITE: https://umra-staging.maxfierke.xyz/login
https://retirees.umn.edu/login

## 1 Open
Enter & open registration
1 | Click on Manage Monthly Programs --> | 2 | It takes you here where you can scroll to the bottom of the page ---> | 4 | Fill out the fields on this form to enter the Luncheon into the system.
To OPEN registration, check the "Registration open" check box. This should only be done just before the newsletter comes out.
|  | 3 | And click on + Add New Program -->

## 2 Monitor
Monitor registrations
1 | Click on Manage Monthly Programs --> | 2 | It takes you here, where you can click on the ROSTER button | 3 | On the Roster you can view who is signed up, if they have paid, or cancel (7) their reservation (click the red Remove button)
You can also export the list by clicking on the Export as CSV button at the bottom of the page
Here is where you download the CSV when you want the list of registrants for a mail merge
The "Remove" button has been changed to an "Edit" button!!!!

## 3 Add
To Add a reservation (paid by check):
1 | Click on Manage Manage Transactions --> | 2 | It takes you to this Transactions screen. | 4 | Fill in this form to create a luncheon payment. Transaction Type is LUNCHEON FEE. | 5
|  |  | To add a single reservation, click "+Add" to enter one person. (-->4) |  | Choose AWAITING PROCESS if they reserve and will pay by check. Put the reservation in, and record payment when it arrives
|  |  | Or you can click "+Add multiple" to add multiple -- this is faster if you have several to enter. (---->5) |  | Multiple member names can be entered together if they are all paying the same amount, with the same payment method. Transaction Type is LUNCHEON FEE. Status is AWAITING PROCESS.
|  | 3 | This screen can also be used to search for reservations you want to change.
If you search for people, their reservation information will show up below.

## 4 Recheck
Rechecking can be done two different ways.
Method 1 | View the Roster information (see tab 2 Monitor)
Method 2 | Or in the Manage Transactions area, search for everyone, described in this tab. You will see slightly different information.]
1 | Click on Manage Manage Transactions --> | 2 | It takes you to this Transactions screen. Use this screen to search for reservations you want to change. | 4 | EDIT a transaction on this form. You can change any field of the transaction.
|  |  | Enter the date range for transactions you want to see. Transaction type is LUNCHEON FEE; |  | Take care, as pressing the tab key, or up/down arrows has been known to modify fields! If you think you may have changed something by mistake, cancel out.
|  |  | Transaction Status = Any Status; if you want to find a single person, enter a few letters of the last name. |  | You may add a note on the date the Check was received, or change the status to PROCESSED.
Press Search
|  | 3 | Here are results for a search for "Austin" LUNCHEON FEES, although it could be a long list of people. Notice the status is AWAITNG PROCESS, confirming it is unpaid.
Date, transaction type, Amount, name, status, Program can all be seen. And this can be exported by clicking on Export as CSV. If you know you have received the Check, you can press Mark as Processed right here!!
You can also EDIT the transaction if you want to change other things. --> 4

## 5 Payment
Recording payment can be done two different ways. (See tab 4 Recheck).
Method 1 | In the Manage Transactions area, search for registrants. In the results at the bottom of the page, click on "Mark as Processed" to record it paid
Method 2 | Or click on "Edit" and change it there. Here you can make notes on the check being received.

## 6 Download
Downloading the CSV can be done two different ways.
Method 1 | View the Roster information (see tab 2 Monitor) Click Export as CSV button in the bottom right.
Method 2 | Or in the Manage Transactions area, search for everyone (see tab 4 Recheck). Click Export as CSV button in the bottom right. When it opens, SAVE AS…. EXCEL sheet.

## 7 Cancel
Cancelling a reservation
policies | Do we have consistent policies that can be applied? Do we all know what they are? Policies you develop should be listed on the website for all to be aware of: (this page is currently hidden on the website) https://umra.umn.edu/monthly-programs/lunch
Reservation cancellation has two parts:
Step 1 | 1) cancel in our database; (See tab 2 Monitor; step 3)
Step 2 | 2) refund the money, and delete the transaction. The transaction stays after the reservation is removed to record that money needs to be refunded or otherwise handled.
**Refunding money: The treasurer can refund the money easily through PayPal if it was paid online. Otherwise, we can return their check, if we still have it; or ask the treasurer to write a check to the people; or perhaps you want to make a policy to allow people to apply their money to another luncheon in the future.
from max | luncheon transactions should create reservations on the roster, but I think if you remove them from the roster it only removes the reservation, not the transaction (since we still want to know if money was received.) There shouldn't be any delay, though in seeing the changes reflected. I can try to recreate it and see what you're running into.

## TESTING
Task
Char/Diane Open registration
Cathy adds some online registrations to simulate real registrations
Cathy can give you a list of names who you can pretend called or emailed their request to you. Note if there is one person, or two for the luncheon.
Perhaps you want Hostess committee members to call you or email you -- this will more closely simulate the lack of information and confused messages you may receive in real life. You can also ask team members to ask difficult questions, like, "can I cancel this if I cannot come?" When do I need to cancel by? Can I register when I arrive? Where should I park? Is there parking reservations this year? How much does parking cost? Is there a discount for parking? How do I get the discount? Where should I send my check? Can I register now and pay when I arrive? (What will your policy be for those who do not show and did not pay?) [What are some other difficult scenarios you might want to plan for?]
Char/Diane will practice recording reservations received in the database, and monitoring the count